## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Austin Health Strategic Plan | Policy | Austin Health's Strategic Plan 2023-27 will help us achieve our vision to shape the future through exceptional care, discovery and learning.The Plan describes key strategic outcomes that are underpinned by our Purpose, Vision, Values and Guiding Principles. | New | Yes | The Guiding Principle 'Timely access to high quality care' explicitly address the importance of removing barriers to accessing care and promote equity and consistency in our practices. The Guiding Prinicple 'Listen to what our patients and community say' explictily identifies the unique and intersectional needs of our patients. Austin Health commits to ensuring that members of our diverse community will experience inclusive services. | Yes | Our Strategic Plan recognises the broad and varied diversity of our community. As part of the Plan consultation process, we engaged with a diverse range of individual staff and consumers, as well as with a range of community groups. This ensured that a broad, interesectional approach was embedded into the Strategy.
Austin Health Primary Care Strategy 2023-27 | Policy | The Austin Health Primary Care Strategy supports Austin Health’s overall strategy and our purpose of helping people live healthy, productive, and fulfilled lives. It outlines our commitment to improve integration with primary care services, in order to deliver better outcomes for our patients. | New | Yes | The principles of the Primary Care Strategy were updated to explicitly focus on equity for our diverse community. Approach 1.4 explicitly commits to conducting a Genderand Equity Impact Assessments on all initiatives that directly affect our community. | Yes | Austin Health has committed to Gender and Equity Impact Assessments, that have an increased and explicit focus on intersectionality. This aims to embed the intersectional approach into all Gender Impact Assessments undertaken at Austin Health.
Austin Health Digital Health Strategy | Policy | The Austin Health Digital Health Strategy | New | Yes | 2 of the 6 Strategic Outcomes: Patient centric care and Empowered workforce address the need to promote equity among our diverse community and to conduct Gender and Equity Impact Assessments on initiatives that directly impact the public. | Yes | Austin Health has committed to Gender and Equity Impact Assessments, that have an increased and explicit focus on intersectionality. This aims to embed the intersectional approach into all Gender Impact Assessments undertaken at Austin Health.
Proposed Eltham Area Community Hospital design | Service | The proposed Eltham Area Community Hospital is in the planning stage. The Eltham area Community Hospital will be a small public hospital providing range of day hospital and primary healthcare services. Strong links to specialists, community health providers and social support services will ensure more seamless follow-up treatment and support for those who require complex care. | New | Yes | The GIA on the plan for the proposed Eltham Area Community Hospital resulted in multiple changes to the design of the proposed building. This included: improved Aboriginal cultural safety at the building entrance, change to the location of the family violence service relative to the mental health service and to facilitate safe access points, improved access to a secure, child and family-friendly courtyard, improved lighting and line-of-sight around the hospital entrance to improve safety for women, gender diverse people and other vulnerable groups. The GIA also identified a range of considerations relating directly to the operation of the building (outside the scope of this project phase). These considerations were documented and will form the basis of a Gender and Equity Impact Assessment of the operations of the proposed hospital which will be conducted at the appropriate time. | Yes | As part of the GIA, a workshop was held that brought together a range of consumers and staff from diverse backgrounds, together with the building architects, designers, the Austin Health Capital Infrastructure team and the Victorian Health Building Authority. The staff and consumer participants were a very diverse group of various genders and other attributes, including disability, age, sexual orientation and culural backgrounds. The perspectives of all participants directly impacted the future design of the proposed hospital.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Establish an effective governance and accountability framework for progress toward workplace gender equality | In progress | GEAP actions planned under this strategy: 1. Appoint an Executive sponsor to support the delivery of the GEAP (complete) 2. Determine the resources and budget needed to implement and monitor the plan (complete) 3. Establish and maintain annual reporting to staff, executive and Board on the progress of GEAP activities (in progress) 4. Provide regular opportunities for engagement with staff on progress of the GEAP and suggestions for improvement (in progress) Implementation progress to date: - Austin's Chief People and Culture Officer has been appointed as executive sponsor to support the delivery of the GEAP - Human resources have been assigned to oversee GEAP implementation - Director Employee Relations and Diversity & Inclusion, Diversity and Inclusion Manager, Diversity and Inclusion Business Partner, a Gender Impact Assessment Manager (see further notes below on GIA) project team work to date - A Gender Equality Working Group was established (with Terms of Reference) in September 2022, with monthly meetings (agenda and minutes stored and shared). This working group provides the mechanism for ensuring all actions outlined in the Gender Equality Action Plan are met within the required timeframes. Membership of the working group includes action owners outlined in the plan. - The Strategy, Performance and Improvement team has been assigned the role of leading implementation of Gender Impact Assessments (GIA) at Austin Health, reporting through to the Executive Director Strategy, Performance and Improvement and to the Austin Health Executive. The GIA Project Team meets monthly and includes representatives from a wide range of Austin Health departments, including Strategy and Planning, Improvement, Capital and Infrastructure, policy, research and various operational units. A project lead has been appointed to lead the implementation work. - Supply agreement with GenderWorks Australia to support actions from the Gender Equality Action Plan, the 2021 and 2023 Workplace Gender Audit Progress Report, including comparative analysis of FY21 and FY23 workforce and employee experience (People Matter) data ‑ Reporting lines to board established, including February 2023 paper to Executives and People and Culture Board Sub-Committee including February 2023 & October 2023 papers to Executives and People and Culture Board Sub-Committee, in preparation for 2023 Progress audit report to the Commission. - Austin Health’s Diversity and Inclusion practitioners and Strategy, Performance and Improvement team are active participants in the Victorian Health Organisations Gender Equality Network (VHOGEN). VHOGEN has provided opportunities to share experiences and learning with public health services from across Victoria and to hear regularly from Dr Niki Vincent, Public Sector Gender Equality Commissioner for Victoria and other Commission staff. This has provided greater insight into the Commission’s governance and delivery standards, learnings from other members and collaboration to provide a consistent approach across the Victorian public hospital sector. |  | 1/07/2022 & 30/06/2024 | Chief People and Culture Officer | x | x | x | x | x | x | x
Create a shared understanding of gender equality across Austin Health | In progress | GEAP actions planned under this strategy: 5. Embed and communicate the importance of and outcomes sought by the Gender Equality Act, the GEAP and Gender Impact Assessments (GIA) across all levels of the organisation (in progress) 6. Develop a communications plan to engage and educate staff around gender equality, including workplace gender equality and GIAs (in progress) Implementation progress to date: - 2021, 2022 & 2023 International Women's Day acknowledged and celebrated with Executive Sponsorship and external MC and Keynote Speakers. Annual Communication Plans with a range of internal and external communications developed and implemented for each annual event, award nominations process and outcomes. Award recipients announced and celebrated. Links to the Gender Equality Act, GEAP and GIA were communicated across the organisation. - In October 2022, a draft of Communications Plan developed with reference to gender equality. This plan has been delegated to a Senior Communications person. |  | 2024-06-30 | Director, Corporate Communications | x | x | x | x | x | x | x
​Improve data collection capabilities across the seven gender equality indicators | In progress | GEAP actions planned under this strategy: 7. Document systems limitations for full and complete workplace gender audit data collection (complete) 8. Resource and implement priority improvements to ensure improved reporting capability in future reporting periods (in progress) 9. Run an annual campaign to encourage people to update their personal details, in line with audit requirements (in progress, ongoing on an annual basis) Implementation progress to date: - In the FY21 baseline audit, Austin Health used employee data from Chris21 and Mercury to complete the ‘Employee’ tab in the 2021 baseline audit, identifying a number of systems collection and reporting limitations. Intention following baseline audit was to make incremental progress on improving data collection in FY23 and subsequent progress audits (FY25, FY27 etc) - Data collection improvements are now being integrated into the new Human Resources Information System (HRIS) project, delivering improved reporting capability and dashboard for ongoing monitoring. - In May 2023, limitations for collecting diversity variables (in line with GE legislation - Aboriginality, disability, cultural identity, gender identity, religion, sexual orientation) were identified by consortium of hospitals involved in HRIS/Success Factors system upgrades. Austin contributed to a paper with recommendations on what diversity variables should be collected and how demographic questions should be asked. These have been submitted to SuccessFactors. |  | 2024-06-30 | Director, HR Shared Services | x | x | x | x | x | x | x
Strengthen leadership capability and confidence to lead a gender equitable and inclusive workforce | In progress | GEAP actions planned under this strategy: 10. Embed gender equality content into the new employee and new manager induction programs (in progress) 11. Update position descriptions for leaders to embed commitment to workplace gender equality (complete) 12. Include gender equitable training in our leadership training module (complete) 13. Embed gender equitable and inclusive leadership measures into manager’s performance review and development plans (not yet commenced) Implementation progress to date: - ​In May 2023, the Frontline Leadership Program commenced. This training includes diversity and inclusion concepts and discusses the benefits of these concepts for developing highly effective teams. - In March 2023, position descriptions for leaders were reviewed by talent acquisition team and updated templates now available on Pulse ​- In November 2022, Austin piloted a three-hour Inclusive leadership training online course to 14 Executive members and senior leaders. The course was developed and delivered by consultant Bree Gorman and a number of topics were presented including unconscious bias. - In May, June & July 2023-The three-hour Inclusive leadership training online course was delivered to leaders, clinical and non-clinical. | Approximately 80 leaders completed the Frontline Leadership Program. Particpants reported that the content was relevant and they could use the new skills and knowledge in their work. -14 Executives attended the Pilot Inclusive Leadership Online Course Most participants agreed that the facilitator demonstrated sound knowledge and that the session should be delivered to leaders across the organisation. -The Inclusive Leadership Training Course was deleiverd four times to over 107 leaders. Most participants agreed that the facilitator demonstrated sound knowledge and the most valuable part of the training session was interaction and sharing and strategies on mitigating bias. Many believed that the breakout rooms were a safe place for discussion that the session should be delivered to leaders across the organisation. | 31/12/2023, 01/09/2023, 01/02/2024 & 30/06/2024 | Organisational Development Manager | x
​Embed gender targets in identified operational teams, divisions and across workforces | Not started | GEAP actions planned under this strategy: 14. Establish a working group to led and implement this initiative and provide advice and recommendation to Executive (not yet commenced) 15. Create a plan for embedding realistic targets and making measurable progress (not yet commenced) 16. Create a Workplace Gender Equality dashboard to track implementation across business units, teams and workforces (not yet commenced) Implementation progress to date: - work has not yet commenced under this strategy |  | 2024-06-30 | Diversity and Inclusion Manager | x
​Increase diversity across leadership cohorts | In progress | GEAP actions planned under this strategy: 17. Ensure flexible work strategies include targeted actions to offer part-time and flexible working arrangements at all leadership levels (in progress) 18. Identify and implement advancement strategies for increasing diversity such as mentoring, scholarships, development and education pathways and secondment opportunities (in progress) Implementation progress to date: - New flexible working arrangements drafted, procedure with CPCO for approval. - New procedure aligned with Fair Work Act expectation and explicitly provides for flexibility at all levels and as no barrier to career development or opportunities. - Training session to HR Consulting, Employee Relations and other P&C scheduled for 2/11/23 (next progress reporting) to explain requirements and best practice for managing and advising on workplace flexibility. |  | 2024-06-30 | Director Employee Relations | x |  |  |  |  | x
Strengthen board members’ capability and confidence to promote workplace gender equality at Austin Health | In progress | GEAP actions planned under this strategy: 19. Identify opportunities for Board to engage in and support gender equitable strategies (not yet commenced) 20. Provide opportunities for Board to attend the gender equitable training in our leadership training module (not yet commenced) 21. Include workplace gender equality as a regular agenda item in the People & Culture Board sub-committee (Ongoing) Implementation progress to date: - 2021-Presentation to Board on Gender Equality Act and obligations under the Gender Quality Act - Feb 2023-Update Report submitted to People and Culture Board Sub-Committee |  | 2024-06-30 | Chief People and Culture Officer |  | x
Diagnose the status of pay equity at Austin and set goals to address areas of concern | In progress | GEAP actions planned under this strategy: 22. Establish a working group to lead and implement this initiative and provide advice and recommendations to Executive (complete) 23. Conduct an organisational wide gender pay gap analysis drawing on the Commission guidance on classification levels for the health sector (in progress) 24. Develop a plan for making measurable progress on priority areas of concern (in progress) 25. Summarise findings and share broad outcomes and goals with the organisation (in progress) Implementation progress to date - first phase of this work is underway and includes pay equity analysis for employees in senior management roles on management contracts, across all directorates, excluding CEO and Executives. - GenderWorks Australia engaged to support Austin with gender pay gap analysis. Austin drew on CGEPS guidance for health sector classifications, to classify senior management roles and map levels of seniority across 5 professional cohorts: Nursing, Medical, Allied Health, Operations, Corporate (including People & Culture, Finance and Infrastructure & Services). Austin intends to focus on Senior Medical Staff and NUMS cohort. Data collection and development of analysis dashboards in progress. |  | 2023-06-30 | Director Employee Relations |  |  | x
Take positive action to reduce gender pay gaps | In progress | GEAP actions planned under this strategy: 26. Increase understanding and awareness of key pay equity concepts among stakeholders and leaders (in progress) 27. Incorporate relevant pay equity metrics into the Workplace Gender Equality dashboard (in progress) 28. Provide managers with the tools and training to understand and address factors within their control to assist with reducing identified gender pay gap (in progress) 29. Consider establishing a discretionary fund to redress any individual pay gaps (in progress) 30. Monitor and report on progress to all stakeholders (in progress) Implementation progress to date - while diagnosis of gender pay gaps continues (strategy in row above), we have commenced work on initiatives to improve gendered outcomes through promotion of superannuation, salary sacrifice and novated leasing opportunities to increase take-home salary. - re: superannuation equity - From Jan 2023, Superannuation funds, with whom Austin Health has a relationship, delivered 26 information sessions to staff on a range of 'Super fit’ topics. The sessions were delivered as 1:1 consults, webinars or public seminars. Four of the sessions specifically targeted women and included topics such as 'Super women: starting your financial journey’, ‘Super women: taking control of your finances’ and ‘Super women: supercharge your super’. A number of sessions also targeted older people and those preparing for retirement - Likely that Action 29 (discretionary fund) will transition to next GEAP. |  | 2024-06-30 | Chief Executive Officer, Diversity and Inclusion Manager |  |  | x
Build a positive workplace culture free from sexism, racism, homophobia, transphobia and discrimination in favour of able-bodied people. | In progress | GEAP actions planned under this strategy: 31. Reinforce clear expectations for all staff, patients and visitors to ensure respectful workplace behaviours (ongoing) 32. Establish a plan for regular zero tolerance messaging from executive and senior leadership (ongoing) 33. Designate key staff with responsibility for maintaining up-to-date knowledge on sexual harassment laws, policies and practices (ongoing) 34. Provide sexual harassment prevention training and education for senior management (in progress) 35. Deliver Gender Equity and Bystander training across the organisation (in progress) Implementation progress to date - Communications have been sent to all staff reminding them about respectful workplace behaviours from Director ER and D&I - In November 2022, Prevention and Management of Sexual Harassment by Patients to Staff policy designed and implemented. Endorsed by Aggression Management Committee and contributed by Workforce Health, and Safety and Wellness Department. - In June 2023, a short session on sexual safety was run on 3N with approximately 15 people in attendance. - In June 2023, Austin became a supporter of 'Racism. It Stops with Me' (Australian Human Rights Commission national campaign) - Re: additional Sexual Harassment & GE and Bystander training - Given the volume of different trainings across the GEAP (including GE and Bystander training under this strategy), Austin's Gender Equality Working group have been on mapping of internal training courses and discussions with external training suppliers to fully equip Austin Health to deliver its obligations relating to gender equality and inclusive practice. The GE working group conducted an analysis of all related employee training requirements and considerations (eg. considerations - connecting new training with Austin's existing 'Living the Values' elearn module, embedding any new content into mandatory new employee and new manager training, integrating GE content into current internal leadership training, considering annual subscriptions or license options through AHRC or Diversity Council Australia, procuring specialist training suppliers, encouraging personal development through external providers of conferences and workshops). The GE Working Group have devised an initial list of training topics for coverage across GEAP implementation, topics including those listed below. • Broader diversity, equity and inclusion awareness training (for all) • Understanding of gender equality and gender equity – What does it mean to me and my role? • Intersectionality – What does intersectionality mean and how does it apply to my role? (for all) • Specialist training on the disadvantage or discrimination that a person may experience on the basis of other diversity attributes or characteristics (also known as intersectionality) such as, Aboriginality, age, disability, ethnicity, gender identity, race, religion sexual orientation (for all) • Inclusive leadership practices • Gender equitable and Inclusive recruitment practices for leaders / managers • Merit for leaders / managers • Sexual harassment (for all) • Family Violence (for all) • Bystander training (for all) • Unconscious bias (for all) |  | 01/10/2022, 01/04/2023, 01/04/2023, 01/07/2023 | General Counsel, Director Employee Relations |  |  |  | x
Improve the experiences of staff who experience sexual harassment from workplace colleagues | In progress | GEAP actions planned under this strategy: 36. Develop a process to assess complainant's satisfaction with formal complaints process (not yet commenced) 37. Review our sexual harassment response processes and identify practical ways to incorporate victim survivor-centric care and support mechanisms (complete) 38. Pilot recommended alternative care and support options for staff experiencing sexual harassment (in progress) Implementation progress to date - In March 2022, Northern Centre Against Sexual Assault (NCASA) Procedure updated. - In November 2022, Prevention and Management of Sexual Harassment by Patients to Staff Procedure implemented, including survivor-centric care. - In November 2022,Prevention and Management of Sexual Harassment by Patients to Staff Procedure announced via The Pulse, 231 views. - In June 2023 - A short session on sexual safety was run on 3N with approximately 15 people in attendance. |  | 2023-12-01 | General Counsel, Director Employee Relations |  |  |  | x
​Implement a comprehensive workplace approach to prevention and response to sexual harassment from patients | Ongoing | GEAP actions planned under this strategy: 39. Develop an educational toolkit to support leaders and staff responding to sexual harassment from patients (ongoing) 40. Develop a guide for leaders to support staff responding to sexual harassment from patients (ongoing) 41. Roll out training to support employees manage occupational violence and aggression (including sexual harassment) in high-risk areas (ongoing) Implementation progress to date Occupational Violence and Aggression Staff Forums: - Dec 2022, Session 1 - What does zero tolerance really mean? - March 2023, Session 2 - Reporting to police - Is it worth it? - October 2023, Session 3 - Stepping back to step forwards - a better experience together. Occupational Violence and Aggression staff training sessions delivered by MOAT Mental Health Services, include sexual harassment: -During 2021, 699 employees attended 53 OVA training sessions. Groups targeted included: Clinical, Community Visits, Non-Clinical, Graduates, Mental Health and Security. -During 2022, 832 employees attended 58 OVA training sessions. Groups targeted included: Clinical, Community Visits, Non-Clinical, Graduates, Mental Health and Security. -During 2023, 696 employees attended 45 OVA training sessions. Groups targeted included: Clinical, Community Visits, Non-Clinical, Graduates and Mental Health. - OVA resources and tools on dedicated Pulse site. - Improvement made to capture all sexualised incidences as ISR2. - OVA Prevention Committee established 2022, | Occupational Violence and Aggression training evaluation data shows significant support from participants of the content and delivery. Staff are indicating that they feel supported by leaders after OVA events. Staff are indicating that they feel supported by leaders after OVA events. | 2023-06-30 | Director, Health Safety and Wellness |  |  |  | x
Commit to consistent application of gender equitable and inclusive recruitment processes and practices | In progress | GEAP actions planned under this strategy: 42. Review the end-to end recruitment processes with a gender and intersectional lens and implement recommendations arising from the review (ongoing) 43. Develop a guide for hiring managers to educate around gender equitable and inclusive recruitment processes (ongoing) 44. Deliver training to managers to reduce unconscious bias from the recruitment process (in progress) 45. Create and promote messaging defining ‘merit’ at Austin Health (in progress) Implementation progress to date: - future work under this strategy will align with our Strategic Plan initiatives to value diversity and inclusion and to bring richness to our work environment (developing initiatives to increase the diversity of our workforce, strengthen our culture of inclusiveness, build upon our Indigenous strategies and employment plan) - Austin Health is currently working through the implementation of a new applicant tracking system, SuccessFactors. As part of the discovery phase for this project, we collaborated with other health services (Alfred Health, Eastern Health, Western Health, Eye and Ear and Peter Mac) to develop recommendations on the data to be captured at all stages of the candidate experience, based on the requirements outlined of the Gender Equality Act. These recommendations have been implemented and will go live at the project completion. - Recruitment policy and guidelines updated to include reducing bias in recruitment information and guidance around gender representation in interview panels. - A number of resources and tools have been developed for hiring managers, including an online training package ‘Recruitment for Success’, which focuses on Austin Health’s recruitment and selection policy and guidelines, including unconscious bias considerations in the overall process. - In November 2022, Austin piloted a three-hour Inclusive leadership training online course to Executive members and senior leaders. The course was developed and delivered by consultant Bree Gorman and a number of topics were presented including unconscious bias. - In May, June & July 2023-The three-hour Inclusive leadership training online course was delivered four times to leaders, clinical and non-clinical. The course presented on a number of topics including unconscious bias. | -14 Executives and senior leaders attended the Pilot Inclusive Leadership Online Course Most participants agreed that the facilitator demonstrated sound knowledge and that the session should be delivered to leaders across the organisation. -The Inclusive Leadership Training Course was delivered four times to over 107 leaders. Most participants agreed that the facilitator demonstrated sound knowledge and the most valuable part of the training session was interaction and sharing and strategies on mitigating bias. Many believed that the breakout rooms were a safe place for discussion that the session should be delivered to leaders across the organisation. | 2023-12-01 | Chief Executive Officer, Director Workforce Planning and Talent Acquisition | x |  |  |  | x
​Identify and address gendered impacts on access to career progression opportunities | Not started | GEAP actions planned under this strategy: 46. Review access to career progression opportunities through a gender lens (noy yet commenced) 47. Identify specialised leadership and career development programs that support the progression of women, men and gender diverse employees into leadership roles (in progress) 48. Promote career development opportunities to all staff, including part-time and casual staff (in progress) 49. Develop strategies to assist staff with caring responsibilities to progress their career (in progress) Implementation progress to date: - These actions were not yet commenced as at end reporting period FY23. |  | 2024-06-30 | Organisational Development Manager | x |  |  |  | x
​Develop a strategic approach to workplace flexibility | In progress | GEAP actions planned under this strategy: 50. Develop guiding principles for workplace flexibility (in progress) 51. Develop a suite of tools and resources to support managers and employees to implement guiding principles (in progress) 52. Promote stories of successful flexible work arrangements across the organisation (not yet commenced) Implementation progress to date: - The update of the Flexible Working Arrangements Procedure has not commenced as at the end reporting period FY23. |  | 2023-06-01 | Director Employee Relations | [5 empty] | x
​Build a culture which supports all employees to access parental leave and return to work support | In progress | GEAP actions planned under this strategy: 53. Review parental leave and carers leave policies with an intersectional gender lens (in progress) 54. Develop a toolkit to guide leaders and staff in the provision of effective parental leave supports throughout the full cycle of leave and return to work (in progress) 55. Develop a process to assess staff satisfaction with parental leave supports (in progress) Implementation progress to date: - The Diversity and Inclusion team has contributed to the Senior Medical Staff parental leave handbook for doctors, aimed at engaging and retaining women and parents of all gender identities as they navigate the complex EBA arrangements around parental leave. - from 6 June 2023, employees also have the right under the Fair Work Act to request flexible work arrangements if they are pregnant or if the Employee or a member of their immediate family or household experiences family and domestic violence. The Flexible Working Procedure has been updated to provide support for employees in these circumstances, and to comply with the new legislation. |  | 01/03/2023, 01/06/2023 & 01/06/2023 | Diversity and Inclusion Manager | [5 empty] | x
​Improve practices related to disclosures of family violence for employees | In progress | GEAP actions planned under this strategy: 56. Review family violence policy with an intersectional gender lens (in progress) 57. Develop a Leaders Guide to responding to disclosures of Family Violence and ensure leaders are appropriately trained (ongoing) 58. Ensure Contact Officers are trained in responding to family violence (in progress) Implementation progress to date: - In December 2022 - published dedicated Family Violence page 'Manager and Staff Support' on The Pulse. - December 2022 - published Family Violence and Sexual Assault information page - April 2023 - Published major update to Family Violence Policy & updated 'Manager and Staff Support' page. | The published dedicated Family Violence page 'Manager and Staff Support' on The Pulse, as at 5/12/2023 had 1965 views and 4 likes. | 30/06/2024, 01/04/2023 & 30/06/2024 | Chief Allied Health Officer, Director HR Consulting | [5 empty] | x
Develop and pilot an approach to address gendered segregation in the workplace | Not started | GEAP actions planned under this strategy: 59. Establish a Working Group to lead and implement this work (not yet commenced) 60. Define target groups based on audit baseline data (in progress) 61. Conduct analysis of enablers and barriers to gender segregation and develop targeted approaches to tackling gender stereotypes and building a safe workplace culture (in progress) 62. Establish targets and timeframes and accountabilities (not yet commenced) 63. Monitor and report on progress (not yet commenced) Implementation progress to date - As at end reporting period FY23, work had not yet commenced under this strategy - As part of our progress audit 2023, we are looking at using some of hte gender composition anlaysis of different ANZSCO cohorts to exploring some potential target groups for future implementation of this strategy |  | 2024-06-30 | Director Employee Relations |  |  |  |  | x |  | x
Take action to address gender stereotypes | In progress | GEAP actions planned under this strategy: 64. Apply a gendered and intersectional lens over corporate collateral (in progress) 65. Set expectations for changes in everyday conversations around respectful language and removing gendered language (in progress) Implementation progress to date - Developed a draft ​Communications and Engagement Strategy within which gender equality has been applied. Examples include Cultural Calendar, articles on The Pulse, D&I calendar of events and promotions, staff profiles from Cultural Calendar shared across the Pulse and social channels |  | 2024-06-30 | Director Corporate Communications, | [6 empty] | x
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
- Austin's Chief People and Culture Officer is executive sponsor, supporting delivery of the GEAP - Director Talent Acquisition oversees GEAP implementation - Diversity and Inclusion Manager & Diversity spends 50% of their time leading and facilitating the implementation and the collection of outcomes of the GEAP strategies and actions - A Gender Equality Working Group (established September 2022) provides the mechanism for ensuring all actions outlined in the GEAP are met within the required timeframes. Membership of the working group includes action owners outlined in the plan. - Austin has a supply agreement with GenderWorks Australia to spend 0.35 FTE to support GE Act implementation (including support with FY21 baseline audit, FY23 progress audit).

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | Comparison of FY21 and FY23 audit results under Indicator 1 suggests limited change, primarily a consistent/stable gender-disaggregated workforce profile across most measures (composition by gender, by gender and employment type, gender and age). Summary findings are reported below. For this progress audit, 'Yes' as reported is based on overall stability; a key change in data collection supporting improved data collection for employees of self-described gender (point 1 in findings below); coupled with genuine attempts to make progress on collection of other intersectional data via joint advocacy with health service providers in FY22/23 (described in column L) Overall findings from progress audit under indicator 1: 1) Notable improvements in gender data collection (self-identification option for employees of self-described gender) Approx 0.1% (5) employees identified as self-described gender in FY21 dataset, up to approx. 0.2% (18) in FY23, due to improved data collection mechanisms/options to update gender to S (self-described). While this may seem a small change, diversity and inclusion, and building an inclusive workplace for people of all genders, has been a key focus for Austin's D&I team. 2) Overall, workforce composition remains relatively consistent for women, men, while reporting for people of self-described gender has increase - 74.6% WOMEN in FY21, 74.0% WOMEN in FY23 - 25.3% MEN in FY21, 25.8% MEN in FY23 - 0.1% SELF-DESCRIBED in FY21, 0.2% SELF-DESCRIBED in FY23 3) Workforce composition by gender and employment type remains relatively stable, FY21 to FY23 Men proportionally over-represented (compared to workforce composition of 25%M) among full-time employees (approx. 35% FT workers are men in FY23, 34% FT workers were men in FY21) Women proportionally over-represented (compared to workforce composition of 75%W) among part-time workers (approx. 82% PT workers are women in FY23, 82% PT workers were women in FY22) 4) Workforce composition by level not useful for comparative analysis, FY21 to FY23 Similar methodology for ‘levels’ used in FY21 to FY23, however data not comparative. Reporting by 'levels to CEO' is a complex process for a large health organisation with multiple professional cohorts. 5) Workforce composition by gender and age remains relatively stable, FY21 to FY23 Overall, general trend toward decreasing proportion of women as age increases Women proportionally over-represented in 15-24 yrs. & 25-34 yrs. Men proportionally over-represented among 65 yrs.+ cohort 6) Workforce composition by Aboriginal/and or Torres Strait Islander identity Similar numbers identifying as Aboriginal and/or Torres Strait Islander (n=34 in FY23, n=38 in FY21)Austin has strong engagement with employees of Aboriginal and/or Torres Strait Islander identity from recruitment onwards, via D&I team Genuine attempts by Austin to make progress include advocacy for improved data collection. 7) Work being done in partnership with other health service providers to ensure new HRIS/Success Factors has improved capacity to collect and reporting on intersectional data in future audits - Although no immediate (FY23) improvements in reporting on intersectionality (beyond gender identity improvements) there are a number of key other progress under GEAP actions focused on Improve data collection capabilities across the seven gender equality indicators. For example, business Case has now been approved in principle to move from existing Mercury and Chris21 platforms to purchase enhanced reporting tools for SAP SuccessFactors from 2 vendors. Austin Health has been part of a consortium of hospitals who identified limitations of diversity variables identified, and contributed to a paper written with recommendations on what diversity variables should be collected and how questions should be asked. These have been submitted to SuccessFactors. | No | No | No | No | No | No | Yes | (g) Genuine attempts made by the defined entity to make progress In the first two years of our GEAP, a key focus under Indicator 1 has been to improve data collection capabilities in line with audit requirements (GEAP actions in progress include Resource and implement priority improvements to ensure improved reporting capability in future reporting periods and running an annual campaign to encourage people to update their personal details,. While Austin has made improvements to gender data collection, allowing for and promoting self-identification of employees of self-described gender, we have also contributed to joint advocacy (with VHOGEN counterparts) for improved D&I data collection capabilities in the new HRIS/Success Factors system upgrades being rolled out across Victorian public health services/hospitals. In FY22/23, limitations for collecting diversity variables (in line with GE legislation - Aboriginality, disability, cultural identity, gender identity, religion, sexual orientation) were identified by consortium of hospitals involved in HRIS/Success Factors system upgrades. Austin contributed to a paper with recommendations on what diversity variables should be collected and how demographic questions should be asked. These have been submitted to SuccessFactors.
Gender composition of governing bodies | Yes | Austin Health Board composition already achieves gender targets. In FY21 baseline audit and FY23 progress audit, Austin's governing body has 9 members - 5 WOMEN:4 MEN, led by male chair. | No | No | Yes | No | No | No | No | (c) Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth Given Victorian health services boards are appointed by the Minister for Health, Austin has no internal influence over shifting composition of board members.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | Comparison of FY21 and FY23 audit results under Indicator 3 suggests some progress against a number of measures under Indicator 3 (small reduction in org-wide MEAN pay gaps on base salary and total remuneration, & reduction in mean pay gaps for largest ANZSCO cohorts - which account for 87% of workforce). For this progress audit, a report of progress is based on these changes, as well as genuine attempts to make progress on diagnosing and tracking the gender pay gap (Column L) 1) Org-wide MEAN gaps have decreased slightly Org-wide MEAN gap on annualised FTE base salary was 29.0% in FY21, now 28.9% in FY23 Org-wide MEAN gap on total remuneration was 28.1%, now FY21 to 27.9% in FY23 2) MEAN gaps have reduced for two largest ANZSCO workforce cohorts For Professionals (primarily Health Professionals), who constitute 80% of the reported workforce – mean gender pay gap on total remuneration has reduced from 2.9% favouring men in FY21 to 1.2% favouring men in FY23. For Labourers (primarily Commercial Housekeepers), who constitute 7% of the reported workforce – mean gender pay gap on total remuneration has reduced from 0.5% favouring men to -0.1% favouring women We also note other audit findings (not constituting progress during this period) as follows: 3) Org-wide MEDIAN gaps have increased slightly Org-wide MEDIAN gap on annualised FTE base salary was 0.0% in FY21, now 0.5% in FY23)Org-wide MEDIAN gap on total remuneration was 6.7% in FY21, now 7.6% in FY23) 4) In FY23 we have not examined by-level reporting gaps in depth, given complexity of defining 'levels' in a large metropolitan health services, as further discussed in Column L. It is likely that future work may not focus on levels, rather professional comparator groups that are more applicable to the Austin Health context, Limitations of Gender Pay Gap Data In a public health service setting (at Austin and across the wide health sector) we need to be aware of the limitations in what organisation-wide gender pay gap data can tell us, given that we have a complex, multidisciplinary workforce (across medical, nursing, allied health, scientist, corporate and operations sectors) governed by multiple Awards and Agreements. While the organisation-wide data is reported to the Commission and published on the Commission's insights portal, it is not a measure that necessarily provides meaningful guidance to Austin on how to address gender pay gaps More useful measures will include gender pay gap within professional cohorts (e.g. nursing, medicine, corporate) and also smaller comparator groups within these professional cohorts (e.g. senior medical staff within medicine). While not published by the Commission, or considered in the standard gender audit reported to the Commission, some of this work (mapping cohorts, exploring gender pay gaps within priority cohorts) is being explored under our current GEAP | Yes | Yes | No | No | No | No | Yes | (a) size of the defined entity, including defined entity's number of employees (b) nature and circumstances of the defined entity, including barriers to making progress Given the both the size (# employees) and diversity (# professional cohorts, #EBA's/craft group agreements governing remuneration) of Austin's workforce, progress under Indicator 3 is incredibly complex. Austin has made the decision to focus on individual cohorts (e.g. senior medical staff) as it begins to explore gender pay gaps. This means org-wide progress is limited in the short-time, as the focus is on defining comparator groups for by-level and like-for-like gender pay gaps. (g) genuine attempts made by the defined entity to drive progress In the first phase of diagnosing the gender pay gap, Austin investigated a significant effort in mapping and classifying senior management roles & levels of seniority, drawing on CGEPS guidance produced specifically for the health sector (mapping levels of seniority across 5 professional cohorts: Nursing, Medical, Allied Health, Operations, Corporate (including People & Culture, Finance and Infrastructure & Services). While this process is ongoing, Austin intends to focus initial analysis on Senior Medical Staff cohort. Data collection and development of analysis dashboards is in progress.
Sexual harassment in the workplace | No | Although quantitative change from FY21 baseline to FY23 progress audit does not provide clear evidence of progress against this Indicator, Austin has made genuine attempts to drive progress under this Indicator (as detailed in Column L). Overall findings from progress audit under Indicator 4: 1) People Matter respondents experience of sexual harassment has increased FY21 to FY2310% of women respondents experienced some form of sexual harassment (up from 9% in FY21)6% of male respondents experienced some form of sexual harassment (up from 3% in FY21)Similar information on experiences was reported in FY23 and FY21. In FY23, most commonly experienced from a client, customer, patient or stakeholder (approx. 1/2 of those experiencing sexual harassment), colleague (approx. 1/3). Most common forms of sexual harassment experienced were sexually suggestive comments or jokes (approx 1/2 reporting harassment experienced this); intrusive questions about private life or comments about physical appearance (approx 1/2 reporting harassment experienced this); inappropriate physical contact (approx 1/4 reporting harassment experienced this); inappropriate staring or leering (approx 1/2 reporting harassment experienced this). Most common responses were to try to laugh it off or forget about it (approx 1/3) or avoid the person(s) by staying away from them (approx 1/3) 2) Number of formal complaints of sexual harassment in the workplace has increased FY21 to FY23In FY23, 228 complaints received, up from 193 in FY21Gender split of complainants is 80%W:20%M (ie.4 in 5 formal reports of sexual harassment are from women).This is comparative to 79%W:21%M split in FY21.In FY23, as in FY21, in approx. 9 in 10 complaints, the respondent was reported as a member of the public or a client/customer/patient/stakeholder In FY23, as in FY21, in approx. 1 in 10 complaints, the respondent was reported as a colleague Although quantitative progress is not clearly evident in audit data above, Austin has made genuine attempts to drive progress against this indicator, as explained in Column L of Indicator progress report. At present we view the increased reporting as representing some form of improvement in reporting systems (awareness of & accessibility of systems) given work we are doing to build and promote awareness of sexual harassment . | Yes | Yes | No | No | No | No | Yes | (a) size of the defined entity, including defined entity's number of employees (b) nature and circumstances of the defined entity, including barriers to making progress Given the both the size (# employees) and diversity (# profressional cohorts) of the workforce, and nature of employee roles (high % in direct service delivery, shift work arrangements) delivery of sexual harassment and other related training and socialisation of updated prevention policies is resource intensive and takes time. This means we would not necessarily expect to see immediate quantative evidence of progress in the first two years of our GEAP. (g) genuine attempts made by the defined entity to drive progress As noted in tab 2.1 Strategies and Measures - Given our current work to address workplace sexual harassment by improving policies, procedures, reporting processes and training to build knowledge, awareness and understanding of what constitutes sexual harassment and how to report it - we believe that an increase in sexual harassment can also, in the short-term, be driven by an increased awareness of what constitutes sexual harassment and how to report it. As we continue to implement GEAP strategies under Indicator 4, we may continue to see reported experience increase in the short-time before decreasing over time’.
Recruitment and promotion practices in the workplace | Yes | Comparison of FY21 and FY23 audit results under Indicator 5 suggests limited changes across recruitment and exit data (see notes below). For this progress audit, 'Yes' as reported is based on overall stability; a key change in data collection supporting improved data collection for employees of self-described gender on recruitment (point 1 in findings below); coupled with genuine attempts to drive progress through GEAP implementation (described in Column L and including policy uptakes, work to address unconscious bias in recruitment information and guidance, development of improved guidance tools to hiring managers) Overall findings from progress audit under Indicator 5: 1) In FY23, gender composition of new recruits remains relatively consistent, with small but evident increase in self-reporting of self-described gender among new recruits (in FY23, gender composition of new recruits is 71.7% W:28.0% M, 0.3% Self-described, compared to FY21 composition of 70% W: 30%M. Improved data collection systems are evident, with increase in representation of people of self-described gender in FY23 recruits (still <10 new recruits, so deeper analysis not possible, but an important increase on FY21, demonstrating improved mechanisms for data collection and promotion of inclusive and respectful workplace for new recruits, promoting self-reporting of diverse gender identities at onboarding stage) 2) In FY23, gender composition of exits shows increased representation of women, now comparative to overall workforce composition (In FY23, gender composition of exits is 73.8%W:26.0%M:0.2% self-described, compared to FY21 composition of 71%W:29%M). Given this shift, exit data is now comparative to overall workforce composition (74.0%W:25.8%M, 0.2%self-described). Note that in FY23 (as in FY21), no data reported on promotions, internal secondments, higher duties, given difficulty of extracting this data as per Commission requirements/definitions. (ie. data not easily tracked in Austin systems) | No | No | No | No | No | No | Yes | (g) genuine attempts made by the defined entity to drive progress Although limited progress evident in overall workforce data FY21 to FY23, genuine attempts to drive progress include GEAP strategies and actions to improve recruitment and promotion processes and address unconscious bias in the recruitment process. This work is reported in tab 2.1 GEAP strategies and measures and includes implementation of a new applicant tracking system, Success Factors; updates to Recruitment policy and guidelines to include reducing bias in recruitment information and guidance around gender representation in interview panels; and development of new resources and tools for hiring managers, including an online training package ‘Recruitment for Success’, which focuses on Austin Health’s recruitment and selection policy and guidelines, including unconscious bias considerations in the overall process.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | Comparison of FY21 and FY23 audit results under Indicator 6 suggests limited changes across recruitment and exit data (see notes below). For this progress audit, 'Yes' as reported is based on strong progress in terms of uptake of family violence leave and Austin's improved systems to support employees requiring family violence leave to access their full entitlements, as well as other safety supports. 1) Increase in uptake of family violence leave In FY23, 55 instances of family violence leave uptake were reported, up from 29 instances of family violence leave uptake reported in FY21. This increase in uptake represents progress in terms of awareness of systems and engagement of Austin contact officers in supporting employees experiencing family violence to seek support and access leave entitlements available to them. Conversations with family violence contact officers have also provided access to other supports beyond leave entitlements, including onward referrals to specialist service providers, support to establish and review safety plans in the workplace. We also note other audit findings as follows: 2) No comparison possible for formal flexible working uptake in FY21/FY23 In FY23 (as in FY21), no data reported on formal flexible work arrangements, given difficulty of extracting this data as per Commission requirements/definitions. (ie. data not easily tracked in Austin systems) 3) LImited comparability of parental leave uptake in FY21/FY23 Note also that comparability of parental leave data reported under this indicator, given slightly different reporting methods in FY21 and FY23. Findings from analysis of parental leave uptake are as follows: In FY23 Composition of paid parental leave uptake is 80%WOMEN:20%MEN, average weeks 2.23 for women, 1.06 for men, 0.2 for self-described gender In FY21, leave uptake data reported slightly differently, overall composition of all parental leave uptake (paid and/or unpaid) was 86%WOMEN:14%MEN (roughly comparative to FY23 data) In FY23, Composition of unpaid parental leave uptake is 94%WOMEN:6%MEN, average weeks 25.33 for women, 1.97 for men In FY21, average weeks taken was also reported slightly differently, overall averages of weeks parental leave taken (paid and/or unpaid) was 30.9 weeks for women, 2.7 weeks for men. This reflects FY23 data patterns, with women much more likely to take significantly longer periods of unpaid parental leave | Yes | No | No | No | Yes | No | Yes | (a) size of the defined entity, including defined entity's number of employees (b) nature and circumstances of the defined entity, including barriers to making progress Given the both the size (# employees) and diversity (# profressional cohorts) of the workforce, and nature of employee roles (high % in direct service delivery, shift work arrangements) social of new and updated policies and support to managers to implement improved flexible working arrangements is challenging, and a long-term investment that may not demonstrate quantitative progress within a 2 year period. (e) Competing priorities and operational obligations, Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not always able to focus as much investment on GEAP implementation. (g) genuine attempts made by the defined entity to drive progress Although limited progress evident in overall workforce data FY21 to FY23, genuine attempts to drive progress in tab 2.1 GEAP strategies and measures and include updates to the flexible working procedure and improvements to the Senior Medical staff parental leave handbook for doctors, aimed at engaging and retaining women and parents of all gender identities as they navigate the complex EBA arrangements around parental leave.
Gendered segregation within the workplace | Yes | Comparison of FY21 and FY23 audit results under Indicator 7 suggests limited changes across ANZSCO Major groups. For this progress audit, 'Yes' is reported based on slight decrease in gender segregation of largest ANZSCO cohort of Professionals (consituting 80% of reported workforce, primarily Health professionals). Work to shift these cohort compositions will be complex and long-term, starting with foundational work in addressing recruitment unconscious bias in recruitment processes, currently underway as reported under Indicator 5, above. 1) In FY23, as in FY21, gender segregation of Austin's workforce continues to reflect broader social and community trends across health industries and occupations. The majority of our workforce (> 80% in FY21 and FY23) are Professionals (primarily Health Professionals), and this workforce continues to be dominated by women. According to quantative data noted below and available on Commission's insights portal - gender segregation of Professionals cohort has decreased slightly since FY21 (Professionals are 85%W:15%M in FY23, down from 87%W:13%M in FY21) 1 - Managers - in FY23, 62%W:38%M, -5%W/+5%M since FY21 (67%W:33%M) 2 - Professionals - in FY23, 85%W:15%M, -2%W/+2%M since FY21 (87%W:13%M) 3 - Technicians and Trade Workers - in FY23, 71%W:29%M, +6%W/-6%M since FY21 (65%W:35%M) 4 - Community and Personal Service Workers - in FY23, 70%W:30%M, -2%W/+2%M since FY21 (72%W:28%M) 5 - Clerical and Administrative Workers - In FY23, <10/<10W no data to be published. 6 - Sales Workers - N/A, none in Austin workforce 7 - Machinery Operators and Drivers - in FY23, 16%W:84%M, no change since FY21 (16%W:84%M) 8 - Labourers - in FY23, 57%W:43%M, -1%W/+1%M since FY21 (58%W:42%M) While limited progress is evident in overall org-wide ANZSCO cohort numbers, we consider small changes noted above in our largest workforce cohort to demonstrate measureable progress, especially in light of factors noted in column L | No | No | No | No | Yes | No | Yes | (e) Competing priorities and operational obligations, Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not always able to focus as much investment on GEAP implementation. (g) genuine attempts made by the defined entity to drive progress While we are yet to focus our GEAP implementation efforts under Indicator 7 on a particular workforce cohort, our focus in addressing gender segregation is initially driven by implementation of improved recruitment and promotion processes and work to address unconscious bias in the recruitment process. This work is reported in tab 2.1 GEAP strategies and measures and includes implementation of a new applicant tracking system, Success Factors; updates to Recruitment policy and guidelines to include reducing bias in recruitment information and guidance around gender representation in interview panels; and development of new resources and tools for hiring managers, including an online training package ‘Recruitment for Success’, which focuses on Austin Health’s recruitment and selection policy and guidelines, including unconscious bias considerations in the overall process.
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to effectively and efficiently resolve sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled